## Sheet1
Backlog | To do/ Ready | In Progress | Blocked/Waiting | Review/ Inspection | Completed
Design updated kitchen layout (High) | Purchase materials (High) | Demo old flooring (High) | Flooring installation (waiting for delivery) | Inspect electrical work | Room measurements completed
Choose flooring type (Medium) | Prepare rooms (Sub-tasks: move furniture, cover floors) | Install lighting wiring (High) | Plumbing updates (waiting for contractor) | Review installed fixtures | Budget finalized
Select lighting fixtures (Medium) | Schedule contractors (High) | Wall prep (Sub-tasks: patch holes, sand walls) | Painting (waiting for inspection) | Walkthrough for quality check | Material selection approved
Choose paint colors (Low)
Upgrade bathroom fixtures (Medium)
Measure rooms (high)
Confirm budgets (High)